## Project tracker
CUSTOMER PORTAL LAUNCH / MASTER PROJECT TRACKER
Eight-week project • Oct 5–Nov 27, 2026 • Owner: Alex Morgan • Budget: $25,000
PROJECT HEALTH | In progress |  | TOTAL TASKS |  |  | COMPLETED |  |  | PROGRESS
Blue text = editable input • Owner, start/end dates and task IDs match the charter • Dependencies are references only (they do NOT automatically move dates)
ID | Task / deliverable | Owner | Phase | Start date | End date | Status | Priority | Predecessor ID(s) | Notes / acceptance criteria | Days
P01 | Requirements and project charter | Alex Morgan | Planning | 2026-10-05 | 2026-10-09 | Complete | High |  | Approved charter and agreed MVP
P02 | Customer requirements intake | Morgan Chen | Planning | 2026-10-06 | 2026-10-13 | Complete | High | P01 | Capture service issues via Google Forms
P03 | Portal UX/UI designs | Jamie Lee | Design | 2026-10-12 | 2026-10-21 | In progress | High | P01 | Desktop and mobile prototype
P04 | Authentication requirements | Sam Taylor | Development | 2026-10-15 | 2026-10-22 | In progress | High | P01 | Use existing authentication provider
P05 | Design review | Jamie Lee | Design | 2026-10-22 | 2026-10-22 | Not started | High | P03 | Review with product and stakeholders
P06 | Design approval | Alex Morgan | Design | 2026-10-23 | 2026-10-23 | Not started | High | P05 | Required before front-end build
P07 | Finalize user testing plan | Morgan Chen | Testing | 2026-10-19 | 2026-10-26 | Not started | Medium | P02 | Recruit testers and define pass criteria
P08 | Account dashboard | Sam Taylor | Development | 2026-10-26 | 2026-11-06 | Not started | High | P06, P04 | Core MVP account summary
P09 | Knowledge base integration | Sam Taylor | Development | 2026-10-28 | 2026-11-10 | Not started | High | P06 | Customer support content
P10 | Internal QA and fixes | Sam Taylor | Testing | 2026-11-09 | 2026-11-13 | Not started | High | P08 | Resolve priority defects
P11 | Security and accessibility review | Morgan Chen | Testing | 2026-11-11 | 2026-11-17 | Not started | High | P08, P09 | Sign-off required before launch
P12 | User acceptance testing | Morgan Chen | Testing | 2026-11-16 | 2026-11-18 | Not started | High | P07, P10 | 80% successful task completion target
P13 | Launch communications | Riley Brooks | Launch | 2026-11-16 | 2026-11-25 | Not started | Medium | P06 | Help center article and customer email
P14 | Go/no-go approval | Alex Morgan | Launch | 2026-11-24 | 2026-11-25 | Not started | High | P11, P12 | Confirm launch readiness
P15 | Customer portal launch | Alex Morgan | Launch | 2026-11-27 | 2026-11-27 | Not started | High | P14 | Go live

## Project timeline
CUSTOMER PORTAL LAUNCH / PROJECT TIMELINE
Visual weekly timeline driven by Project tracker start/end dates • Native Sheets Timeline instructions below
IMPORTANT | This Gantt-style sheet updates from the Project tracker. To capture Google’s actual Timeline view, import workbook and use Insert > Timeline.
Task | Owner | Start | End | Status | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23
HOW TO CREATE THE NATIVE GOOGLE SHEETS TIMELINE VIEW
1. Upload this .xlsx to Google Drive and open it with Google Sheets.
2. Select the Project tracker task table (B7:G22), including task, owner, start/end dates and status.
3. Use Insert > Timeline (available on eligible Google Workspace editions).
4. Set card title = Task / deliverable, start = Start date, end = End date; optionally group by Owner or Phase.
5. Choose a weekly view, then capture that native Google Sheets interface for the article.
Tip: This visual worksheet is a fallback. Neither view automatically reschedules dependent tasks.

## Budget tracker
CUSTOMER PORTAL LAUNCH / BUDGET TRACKER
Illustrative budget for the same $25,000 portal launch
Category | Owner | Planned ($) | Actual ($) | Remaining ($) | Notes
Design & UX | Jamie Lee | 5000 | 2800 |  | Portal design and prototype
Development | Sam Taylor | 12000 | 3800 |  | Dashboard and knowledge base
Testing & accessibility | Morgan Chen | 3500 | 500 |  | QA, security, accessibility
Launch communications | Riley Brooks | 2000 | 0 |  | Emails and help content
Contingency | Alex Morgan | 2500 | 0 |  | Unexpected scope or fixes
TOTAL

## Risks & issues
CUSTOMER PORTAL LAUNCH / RISKS & ISSUES
Illustrative risks and mitigations, aligned with the project charter
ID | Risk / issue | Likelihood | Impact | Owner | Mitigation / next step | Status
R01 | Design approval slips past Oct 23 | Medium | High | Alex Morgan | Schedule Oct 22 review and secure sign-off | Open
R02 | Authentication integration takes longer | Medium | High | Sam Taylor | Confirm existing provider requirements by Oct 22 | Monitoring
R03 | Accessibility issues emerge late | Medium | High | Morgan Chen | Test early and complete review by Nov 17 | Open
R04 | Launch help content not ready | Low | Medium | Riley Brooks | Draft early and review by Nov 25 | Monitoring
R05 | Scope expands to live chat | Medium | Medium | Alex Morgan | Keep live chat explicitly out of MVP | Mitigated